## 11 Oct 2026
PAT Berth Window — Vessel List by Berth — Sheet dated 11 Oct 2026
Berth | Vessel | LOA (m) | ETA | P.B | ETD | Waiting for Berth (h) | Hours Alongside | Shift | Marked
20AB | CNC MARS | 564 | 2026-10-09 22:00 | 2026-10-10 15:00 | 2026-10-11 15:00 |  |  | –
20AB | SAMAL | 564 | 2026-10-12 09:00 | 2026-10-12 16:00 | 2026-10-14 05:00 |  |  | –
20AB | CEBU | 564 | 2026-10-13 | 2026-10-14 06:00 | 2026-10-15 16:00 |  |  | – | Yes
20B | XIN MING ZHOU 102 | 564 | 2026-10-10 21:00 | 2026-10-11 05:00 | 2026-10-12 02:00 |  |  | –
20B | WAN HAI 277 | 564 | 2026-10-12 23:00 | 2026-10-13 06:00 | 2026-10-14 15:00 |  |  | – | Yes
20C | STARSHIP AQUILA | 565 | 2026-10-09 22:00 | 2026-10-10 14:00 | 2026-10-12 02:00 |  |  | –
20C | KMTC TAIPEIS | 565 | 2026-10-13 01:00 | 2026-10-13 05:00 | 2026-10-14 15:00 |  |  | –
20D | INCEDA | 564 | 2026-10-10 17:00 | 2026-10-11 06:00 | 2026-10-12 14:00 |  |  | –
20D | SAWASDEE SUNRISE | 564 | 2026-10-12 09:00 | 2026-10-12 16:00 | 2026-10-14 05:00 |  |  | –
20D | KHUNA BHUM | 564 | 2026-10-13 07:00 | 2026-10-14 05:00 | 2026-10-14 22:00 |  |  | 7B | Yes
20F | SAWASDEE ATLANTIC | 564 | 2026-10-07 20:00 | 2026-10-09 15:00 | 2026-10-11 12:00 |  |  | –
20F | JOSCO SHINE | 564 | 2026-10-12 09:00 | 2026-10-12 15:00 | 2026-10-13 06:00 |  |  | – | Yes
20F | ALS SUMIRE | 537 | 2026-10-12 22:00 | 2026-10-13 06:00 | 2026-10-14 06:00 |  |  | 1C
Berth & gate notices on this sheet
Berth / Gate | Type |  | From | To | Notice / change vs previous sheet
20D | Berth closed |  | 2026-10-04 | 2026-10-24 | Close on 4–24 Oct 2026 to renovate electric channel (INCEDA is alongside at 20D; other vessels are booked from 12/09) — Unchanged – conflicts with vessel bookings, please confirm
20E / G.25 | Gate stopped |  | 2026-10-05 | 2026-10-18 | G.25 stops working 5–18 Oct 2026 to change trolley rail (in progress) — Unchanged