## 14 Oct 2026
PAT Berth Window — Vessel List by Berth — Sheet dated 14 Oct 2026
Berth | Vessel | LOA (m) | ETA | P.B | ETD | Waiting for Berth (h) | Hours Alongside | Shift | Marked
20AB | KMTC TAIPEIS | 565 | 2026-10-13 02:00 | 2026-10-14 05:00 | 2026-10-15 08:00 |  |  | –
20AB | WAN HAI 176 | 564 | 2026-10-15 11:00 | 2026-10-15 11:00 | 2026-10-16 16:00 |  |  | –
20B | CEBU | 564 | 2026-10-12 22:00 | 2026-10-13 06:00 | 2026-10-14 13:00 |  |  | –
20B | M ODYSSEY | 449 | 2026-10-14 01:00 | 2026-10-14 15:00 | 2026-10-15 05:00 |  |  | 4A
20B | KHARIS HERITAGE | 482 | 2026-10-15 01:00 | 2026-10-15 07:00 | 2026-10-16 07:00 |  |  | –
20C | WAN HAI 277 | 564 | 2026-10-12 21:00 | 2026-10-13 06:00 | 2026-10-14 16:00 |  |  | –
20C | WAN HAI 173 | 565 | 2026-10-14 01:00 | 2026-10-14 16:00 | 2026-10-15 07:00 |  |  | –
20C | WAN HAI 175 | 565 | 2026-10-14 23:00 | 2026-10-15 07:00 | 2026-10-16 15:00 |  |  | –
20D | KHUNA BHUM | 564 | 2026-10-13 11:00 | 2026-10-14 05:00 | 2026-10-14 22:00 |  |  | 7B
20D | SITC DALIAN | 470 | 2026-10-14 08:00 | 2026-10-15 05:00 | 2026-10-16 06:00 |  |  | –
20D | WAN HAI 172 | 565 | 2026-10-16 01:00 | 2026-10-16 07:00 | 2026-10-17 15:00 |  |  | –
20F | SAWASDEE INCHEON | 564 | 2026-10-13 15:00 | 2026-10-14 06:00 | 2026-10-16 06:00 |  |  | –
Berth & gate notices on this sheet
Berth / Gate | Type |  | From | To | Notice / change vs previous sheet
20D | Berth closed |  | 2026-10-04 | 2026-10-24 | Close on 4–24 Oct 2026 to renovate electric channel (KHUNA BHUM is alongside at 20D; other vessels are booked from 15/05) — Unchanged – conflicts with vessel bookings, please confirm
20E / G.25 | Gate stopped |  | 2026-10-05 | 2026-10-18 | G.25 stops working 5–18 Oct 2026 to change trolley rail (in progress) — Unchanged