## 03 Oct 2026
PAT Berth Window — Vessel List by Berth — Sheet dated 03 Oct 2026
Berth | Vessel | LOA (m) | ETA | P.B | ETD | Waiting for Berth (h) | Hours Alongside | Shift | Marked
20AB | RESURGENCE | 458 | 2026-10-03 12:00 | 2026-10-03 12:00 | 2026-10-04 17:00 |  |  | –
20AB | ZHONG GU BEI HAI | 561 | 2026-10-04 09:00 | 2026-10-04 15:00 | 2026-10-06 10:00 |  |  | – | Yes
20B | YM IMPROVEMENT | 564 | 2026-10-03 23:00 | 2026-10-04 10:00 | 2026-10-05 12:00 |  |  | –
20B | JOSCO LUCKY | 564 | 2026-10-05 22:00 | 2026-10-06 12:00 | 2026-10-07 13:00 |  |  | –
20C | SAWASDEE DENEB | 564 | 2026-10-05 | 2026-10-05 12:00 | 2026-10-07 12:00 |  |  | –
20D | HARI BHUM (Barge) | 259 | 2026-10-03 05:00 | 2026-10-03 07:00 | 2026-10-03 16:00 |  |  | –
20E | WAN HAI 278 | 564 | 2026-10-02 22:00 | 2026-10-03 10:00 | 2026-10-05 11:00 |  |  | –
20F | KMTC BANGKOK | 564 | 2026-10-02 07:00 | 2026-10-02 11:00 | 2026-10-03 17:00 |  |  | –
20F | XIN MING ZHOU 98 | 564 | 2026-10-04 09:00 | 2026-10-04 09:00 | 2026-10-05 09:00 |  |  | –
Berth & gate notices on this sheet
Berth / Gate | Type |  | From | To | Notice / change vs previous sheet
20C | Berth closed |  | – | 2026-10-05 | Wharf will be utilised on 5 Oct 2026 — Unchanged
20C | Cable splicing |  | 2026-10-04 09:00 | 2026-10-04 12:00 | 20C and 20D cable splicing on 4 Oct 2026, 09:00–12:00 — New (berthing-section sheet)
20D | Cable splicing |  | 2026-10-04 09:00 | 2026-10-04 12:00 | 20C and 20D cable splicing on 4 Oct 2026, 09:00–12:00 — New (berthing-section sheet)
20D | Berth closed |  | 2026-10-04 | 2026-10-25 | 20D closed 4–25 Oct 2026 to renovate electric channel (cable track bays 1700–1800) — End moved 24 → 25 Oct (the feeder sheet of the same day still says 24)
20E / G.25 | Gate stopped |  | 2026-10-05 12:00 | 2026-10-18 | G.25 stops working from 5 Oct 12:00 to change trolley rail (bays 700–900); end date is cut off on this sheet, daily sheet says 18 Oct — Start time added (12:00); end date unclear